Thomas.Renz@rl.af.mil, Robert.Kaminski@rl.af.mil, skumar@darpa.mil, jmartin@snap.org

Quarterly Report for the period 1 Oct 02 - 31 Dec 02

1.  The recipient shall submit quarterly reports on or about the 15th of January, April, July, and October.  One copy each shall be provided to the following persons as listed in Article 5, Administrative Responsibilities.

The July report, Project Summary Report, shall provide a project summary and shall, in addition to the distribution shown below, be posted to a web site to be designated by DARPA.

(a)  Air Force Research Laboratory (or Navy) Program Manager

(electronic only;  MS Office-compatible)

(b)  Grants Administration Office.

(c)  Air Force Research Laboratory (or Navy) Grants Administrator (or the AFRL

Grants Officer, if no AFRL Grants Administrator is listed in Article 5)

(d)  DARPA Program Manager(electronic only;  MS Office-compatible)"

The report will have two major sections; the Technical Status Report and the

Business Status Report (see (a) and (b), below, respectively).

(a)  Technical Status Report.  The technical status report

will detail technical progress to date and report on all problems, technical

issues, or major developments during the reporting period.  Each of the

topics described below shall be addressed:

(i)  A comparison of actual accomplishments with the

goals and objectives established for the period, the findings of the

investigator, or both.

Milestones from the 22-Aug-2001 goals are discussed below.

"2#4: An early milestone in the highest speed & resolution method proposed here will be the incorporation of a fluorescent nucleotide triphosphate by T7 RNA polymerase under control of a caged ATP or GTP. (Dr. Mitra)

We have contacted 5 potential collaborating groups to address synthesis of reversibly blocked dNTPs.

"3#1: The construction of three-dimensional arrays of DNAs and polymerases will initially build on our "polony" technology [*Mitra 1999]. A method for fluorescent in situ sequencing in such 3D polyacrylamide arrays will be developed using chemically cleavable dNTPs. (Dr. Mitra)

As mentioned in the Apr 02 report, the lower costs, higher density, and more likely progress of the single bp memory (2#4, 3#1-3) over recombinational methods continue to guide our prioritization of the former as project goals.  We have made considerable progress on the polony read-out methods for DNA haplotypes (in review at PNAS), RNA splicing (MS in prep), and DNA sequencing (also in review).  Software for image analysis of the polony sequences capable of individual pixel sequencing shows accurate alignment over 10 cycles of dNTP addition to 0.4 pixel precision.

3#2: Photocleavable versions of the above will be tested. (Dr. Mitra)

The photocleavable versions have not yet proven superior to the redox cleavable bonds.  Several major advances in the polonies include the use of a new crosslinker which allows a new reducing agent and no second acrylamide layer.  This allows faster cycles and less tearing of the polymer coating.  This in turn allowed automation of the process which has resulted in faster protocol development.

"4#1: For the minigenome project, important demonstrations will be the replication dependent in vitro translation of GFP or luciferase using crude  E.coli lysates."

We (Dr. Tian) have demonstrated this for a poly-GFP construct and tested expression clones for ribosomal 30S proteins(in collaboration with Gloria Culver) including now one his6-affinity tagged protein (S15) and one drug-resistance (spc) tagged rRNA.  Antibodies to the his-tag for Western blots are proving to be a reliable assay, and more general than the fluorescent-GFP assay.  So the minigenome genes are being moved into linear his-tag "in vitro" RCA vectors.

"4#4: A SSR or homologous recombination method will be tested for the transfer of genes for expression in minigenomes. "

We have developed a superior strategy of using the linear vectors without recombination since this allows rapid prototyping of relative gene dosage with a broad continuously adjustable range.

"4#5:  We will develop a rolling circle primer immobilization method. (Drs. Tian and Huang)"

This has been done.  The conversion from linear to circular is the basis for our switch to linear vectors (see $#1 above).

"5#3: Software for inclusion of microscopic morphology, dynamics, and stochastics will be developed. "

This has now been done by Wright, Church, Segre and Aach for four different DNA replication scenarios: 3D Mycoplasma chromosome, 4D replication, Hyperbranched Rolling Circle Amplification (HRCA), and immobilized PCR-colony (Polony) models.

We have completed genome sequencing for Mycoplasma mobile and a "probably complete" proteome for M. pneumoniae.  Both very helpful for integration and 4D-modeling efforts.

"5#1: The computational deliverables will be coordinated with other DARPA BIO-COMP participants. "

We have extended FBA to analyze close-to-optimal networks as might occur in mutants.  This extension,  "Minimization of Metabolic Adjustment" (MoMA) is published and being extended to allow automated access to new genomes  (Segre & Vitkup assisted by Jeremy Zuker, Tamar Mentzel, Jeremy Katz, Julian Bonilla, and Shrikant Palaskar).

Peter Karchenko has helped implement a Java MoMA client & server using OAA 2.2 libraries.

Dat Nyugen has assisted in incorporating an open source quadratic programming module. Other BioComp participants, Andrew Finney of Caltech and Mark Johnson of SRI have interacted with our group on this..

"5#3: Software for inclusion of microscopic morphology, dynamics, and stochastics will be developed. (Mr. Wright and/or Mr. Karchenko))"

We have submitted to Biospice & SBML a draft of a 3D modeling of Mycoplasmal chromosome and membrane integrating a variety of experimental and physical constraints.  This will be extended to 4D model by next quarterly report.

(ii)  Reasons why established goals were not met, if appropriate.

The goals were met.  New goals have been added relevant to the BioSpice team efforts (henceforth 5#1a & 5#1b).  5#1a addresses two major limitations of SBML2 which are polymer synthesis and space-time considerations as seen in our 4D-cell model.  5#1b Making our MOMA package compatible with BioSpice 2.1 (we have completed incorporation of an open-source object-oriented quadratic programming package into MOMA).

(iii)  A cumulative chronological list of written publications in technical journals.  Include those in press as well as manuscripts in preparation and planned for later submission.  Indicate likely journals, authors, and titles.

Mitra,RD, Shendure,J, Olejnik,J, Olejnik,EK, and Church,GM (2003) Fluorescent in situ Sequencing on Polymerase Colonies. Submitted to Analyt. Biochem. Dec 2002.

Steffen, M, Jaffe, JD, & Church, GM (2003) Analysis of DNA-Binding Proteins by Mass Spectrometry. Submitted to Nature Biotechnology Oct 2002.

Mitra, RD, Butty, V, Shendure, J, Williams, BR, Housman, DE, and Church, GM (2003) Digital Genotyping and Haplotyping with Polymerase Colonies. Submitted to PNAS on Oct-2002

Jaffe JD, Berg, HC, Church GM (2003) Proteogenomic mapping reveals genomic structure and novel proteins undetected by computational algorithms. Under review at Nature Biotechnology.  Revised version completed.

Lee M-LT, Bulyk ML, Whitmore GA, Church GM. (2003) A statistical model for investigating binding probabilities of DNA nucleotide sequences using microarrays. Biometrics 58(4):981-8.

Segre, D, Vitkup, D, and Church, GM (2002) Analysis of optimality in natural and perturbed metabolic networks.  PNAS 99: 15112-7

Douglas W. Selinger, Rini Mukherjee Saxena, Kevin J. Cheung, George M. Church, and Carsten Rosenow (2003) Global RNA half-life analysis in Escherichia coli reveals positional patterns of transcript degradation. Submitted Jun-2002 to Genome Research.

Sudarsanam,P., Pilpel,Y, and Church, G.M. (2002) Genome-wide co-occurrence of promoter elements reveals a cis-regulatory cassette of rRNA transcription motifs in S. cerevisiae . Genome Research 12: 1723-1731.

Cheung, KJ, Badarinarayana,V, Selinger, D, Janse, D, and Church, GM (2002)A microarray-based antibiotic screen identifies a regulatory role for supercoiling in the osmotic stress response of Escherichia coli. Genome Research  12: 1723-1731

Steffen, M, Petti, A, D'haeseleer, P, Aach,J, and Church, GM (2002) Computational Identification of Signal Transduction Networks. Bioinformatics 3:23.

Wright, M and Church,GM (2002) An Open-source Oligonucleotide Microarray Probe Standard for Human and Mouse. Nature Biotechnology 20(11):1082-3.

Shendure, J & Church, GM (2002) Computational discovery of sense-antisense transcription in the mouse and human genomes Genome Biology 3:1-14.

Schilling, CH, Covert, MW, Famili, I, Church, GM, Edwards, JS, Palsson, BO (2002) Genome-scale metabolic model of Helicobacter pylori 26695. J Bacteriol. 184(16):4582-93.

Dudley, AM, Aach, J, Steffen, MA, and Church, GM (2002) Measuring absolute expression with microarrays using a calibrated reference sample and an extended signal intensity range. Proc. Nat. Acad. Sci. USA 99:7554-7559.

(iv)  A list of professional personnel associated

with the research effort.  List any advanced degrees awarded, including

dates, recipient, type of degree, and thesis title.

Professional Personnel

George Church	Ph.D. Harvard University, Cambridge, MA 1984 Biochem. & Molecular Biology, B.A. Duke University, Durham, NC 1974 Zoology & Chem

John Aach	09/1980-01/1987: Boston University, Boston, MA. PhD Interdisciplinary Studies: Philosophy and Psychology 09/1972-06/1975: Princeton University, Princeton, NJ. AB Music

Allegra Petti	B.A. Biology, cum laude, Rice University, May 1998

Research topic:  Inference of transcriptional regulatory networks from microarray data using nonlinear mathematical models.

# Nikos Reppas   MBiochem. (combination of BA and MA) from Oxford University received June 1998. The MA thesis title is "X-ray Crystallographic Analysis of the Aspartate181->Alanine Substrate-Trapping Mutant of Human Protein Tyrosine Phosphatase 1B (PTP1B) Catalytic Domain".

# Rob Mitra	PHD - MIT 2000, MS - MIT 1993, BS - MIT 1993

Research Topic - High Throughput Sequencing Technology

Jay Shendure  MD/PhD candidate in Harvard BBS program.

Research topic: Polony sequencing

Daniel Segre	2000 : Ph.D. in Life Sciences, Department of Molecular Genetics, The Weizmann Institute of Science, Rehovot, Israel. Advisor: Prof. Doron Lancet. Title: The primordial emergence of compositional inheritance.

(v)  Papers presented at meetings, conferences, seminars, etc.

Oct 2, 2002 Genome Sequencing and Analysis Conference (GSAC) Boston (George Church)

Nov. 8, 2002   University of Massachusetts Boston, Genome "Systems models: Genotype to Phenotype" (George Church).

Dec 9-11, 2002 DARPA Biospice meeting in San Diego, CA (Daniel Segre)

Dec 13-15, 2002 Third International Conference on Systems Biology at the Karolinska Institutet, Stockholm, Sweden (George Church).

(vi)  Consultative and advisory functions to other laboratories and agencies, especially Air Force and other DoD laboratories on research supported under the agreement.  Provide factual information about the subject matter, institutions, dates, and the names of individuals involved.

We have delivered various Biospice software components and updated modules as described above in section 5#1 and 5#3.

We have continued support of our polony technology at another DARPA funded laboratory at the Univ. of Delaware (Directed by Jeremy Edwards) where they have greatly extended the technology toward precise RNA quantitation in yeast.  Two other distribution sites are in progress (at Washington University, directed by Rob Mitra and at TCAG/TIGR directed by Craig Venter in Bethesda, MD).

(vii)  New discoveries, inventions, or patent disclosures and specific applications stemming from the research effort.

We (Greg Porreca, George Church and Jay Shendure) have developed a device to automatically perform the polony sequencing incubations and wash steps.  This has not been submitted for patenting yet.